## Slide 1: Erasmus + Key Action 2 – Co-operation for Innovation and the Exchange of Good Practices
Pupil Health & Well-Being
External evaluation

## Slide 2: Evaluator
Ray Kirtley (plus Ann Brown for this meeting)
Faculty of Education – University of Hull Erasmus + support Evaluative partner in E+ Key Action 3
External evaluator for 2 x Key Action 2 projects
Key Actions 1 & 2 assessor
Global Learning Association (Chair)

## Slide 3: Methodology
Evaluation plan
Internal evaluation – Dr Vassilis Barkoukis Quality guidelines Quality assurance Risk identification and mitigation Self assessment – meetings and work packages
External Impartial overview of project progress – interim and final report

## Slide 4: What’s going well
Group identity and working atmosphere Working together on previous projects has helped to build relationships School-University contacts being strengthened Staff members not directly involved also engaged Partners report positive impact on students Partnership with the gym going well
Co-ordination – effective and friendly
Website and early dissemination

## Slide 5: Potential issues
Communication between meetings Effective? Should other methods be considered?
Project documents – location and editing
Clarity and consistency in module specification, design and presentation
Feedback on draft modules when requested and a common understanding of the timeline for each one?
Translation time and deadlines Are deadlines always clear and always respected?

## Slide 6: The future
Academic outputs – specification and timing Are the research questions defined?
Planning for the Nov 2016 Multiplier
Assessing impact and attributing impact to the work of the project
Benchmarking?
Potential for transferring to other sectors and stakeholders

## Slide 7: Challenging but achievable!